## Executive Summary
Deployment Assistance Tool
Development Plan & Task Breakdown
Generated: 28 May 2026 ¦ Target Stack: JavaScript / TypeScript ¦ CI/CD: GitHub Actions
6 Phases | 43 | 21 Weeks | 19 Tools | $0
Development Phases | Total Tasks | Total Timeline | OSS Tool Stack | License Cost
Phase Overview
Phase | Name | Timeline | Tasks | Milestone
Phase 1 | Foundation — Static Analysis & Container Security | Wk 1-3 (07 Jul - 27 Jul 2025) | 11 | M1: All static analysis and container scanners run in GitHub Actions, producing SARIF output on every PR
Phase 2 | Security Depth — DAST, SCA, IaC Scanning | Wk 4-6 (28 Jul - 17 Aug 2025) | 8 | M2: Full security scanning pipeline (SAST+DAST+SCA+IaC) running in CI with unified output
Phase 3 | Test Intelligence — Automated Generation & Execution | Wk 7-10 (18 Aug - 14 Sep 2025) | 7 | M3: AI-powered test generation running in CI, coverage reporting integrated into pipeline output
Phase 4 | Aggregation — Dashboard & Finding Management | Wk 11-14 (15 Sep - 12 Oct 2025) | 7 | M4: DefectDojo ingesting all scanner results, deployment readiness score computed per project
Phase 5 | Intelligence Layer — Feedback & Org-Specific Tuning | Wk 15-18 (13 Oct - 09 Nov 2025) | 6 | M5: LLM suggestion accuracy tracking live, org-specific Semgrep rules deployed, documentation complete
Phase 6 | LLM Security & Red Teaming | Wk 19-21 (10 Nov - 30 Nov 2025) | 4 | M6: LLM-specific vulnerabilities (Prompt Injection, Jailbreaks) automatically blocked in CI
Architecture Principle
Each module is a standalone scanner wrapper producing SARIF/JSON output. Module 5 (CI/CD) is the glue layer composing modules into parallel pipeline jobs. Module 6 (DefectDojo) is the aggregation layer consuming all outputs. No module depends on another at runtime — they communicate through file artifacts. This design allows incremental adoption: teams can start with Module 1 alone and add modules over time.

## Task Breakdown
Detailed Task Breakdown by Phase
PHASE 1: FOUNDATION — STATIC ANALYSIS & CONTAINER SECURITY
Milestone: M1: All static analysis and container scanners run in GitHub Actions, producing SARIF output on every PR
# | Task ID | Task Name | Description | Effort | Priority | Depends On | Owner | Deliverable | Status
1 | 1.1 | Project Initialisation | Scaffold TypeScript CLI project (package.json, tsconfig, commander setup, config loader) | 2d | Critical | - | Lead Dev | Working CLI skeleton with `dat --help` | Not Started
2 | 1.2 | Scanner Execution Engine | Build child-process wrapper with timeout, exit-code handling, prerequisite checks (is tool installed?), and structured output parsing | 3d | Critical | 1.1 | Lead Dev | Reusable `runScanner()` function with typed results | Not Started
3 | 1.3 | Semgrep Integration | Implement Semgrep scanner module: config generation, rule-set selection (p/javascript, p/typescript, p/security-audit), SARIF output parsing | 2d | Critical | 1.2 | Dev 1 | `dat scan --code-quality` runs Semgrep and outputs findings | Not Started
4 | 1.4 | SonarQube Integration | Docker Compose config for SonarQube Community, sonar-scanner CLI wrapper, quality gate status check via API | 3d | High | 1.2 | Dev 2 | `dat scan --sonar` triggers analysis and reports gate pass/fail | Not Started
5 | 1.5 | PR-Agent Setup | GitHub Action workflow for PR-Agent with LLM provider configuration, self-hosted runner compatibility | 2d | High | 1.1 | Dev 1 | PR-Agent auto-reviews every opened PR | Not Started
6 | 1.6 | Hadolint Integration | Dockerfile linting module: parse Hadolint JSON output, severity mapping, best-practice rule enforcement | 1d | High | 1.2 | Dev 2 | `dat scan --docker-lint` lints all Dockerfiles in repo | Not Started
7 | 1.7 | Trivy Container Scan | Container image scanning module: scan built images for CVEs, OS packages, language deps, secrets | 2d | High | 1.2 | Dev 1 | `dat scan --container-vuln <image>` outputs CVE report | Not Started
8 | 1.8 | Dockle Integration | CIS benchmark scanning for built images, JSON output parsing, pass/fail thresholds | 1d | Medium | 1.2 | Dev 2 | `dat scan --container-cis <image>` outputs benchmark results | Not Started
9 | 1.9 | Result Aggregator v1 | Unified result model: normalise findings from all scanners into common schema (id, severity, source, file, line, message, remediation) | 2d | Critical | 1.3,1.6,1.7 | Lead Dev | Unified JSON output combining all scanner results | Not Started
10 | 1.10 | GitHub Actions Workflow v1 | Composite GitHub Action running all Phase 1 scanners in parallel jobs, uploading SARIF to GitHub Security tab | 2d | Critical | 1.9 | Lead Dev | `.github/workflows/dat.yml` — working CI pipeline | Not Started
11 | 1.11 | Console Reporter | Styled terminal output with severity colors, summary counts, and pass/fail verdict | 1d | High | 1.9 | Dev 1 | Human-readable CLI output with color-coded findings | Not Started
PHASE 2: SECURITY DEPTH — DAST, SCA, IAC SCANNING
Milestone: M2: Full security scanning pipeline (SAST+DAST+SCA+IaC) running in CI with unified output
# | Task ID | Task Name | Description | Effort | Priority | Depends On | Owner | Deliverable | Status
1 | 2.1 | Trivy SCA Module | Dependency vulnerability scanning: parse package.json/package-lock.json/yarn.lock, detect CVEs in node_modules | 2d | Critical | 1.2 | Dev 1 | `dat scan --deps` scans JS/TS dependency tree | Not Started
2 | 2.2 | OSV-Scanner Integration | Google OSV-Scanner for low-noise supplemental dependency scanning, lockfile parsing | 1d | Medium | 1.2 | Dev 2 | `dat scan --osv` as supplemental dep scan | Not Started
3 | 2.3 | Renovate Configuration | Self-hosted Renovate config for automated dependency update PRs: schedule, grouping, automerge rules | 2d | High | - | Dev 2 | `renovate.json` config + GitHub Action for self-hosted runs | Not Started
4 | 2.4 | Checkov IaC Scanner | Infrastructure-as-Code scanning: Terraform, K8s manifests, Dockerfiles, CloudFormation. JSON output parsing. | 2d | High | 1.2 | Dev 1 | `dat scan --iac` scans all IaC files in repo | Not Started
5 | 2.5 | OWASP ZAP Baseline Scan | DAST integration: ZAP baseline scan against staging URLs, API scan mode, HTML/JSON report generation | 3d | High | 1.2 | Dev 1 | `dat scan --dast <url>` runs ZAP against live endpoint | Not Started
6 | 2.6 | Security Headers Checker | Lightweight HTTP header validator: check CSP, HSTS, X-Frame-Options, X-Content-Type-Options, Referrer-Policy, Permissions-Policy | 1d | High | - | Dev 2 | `dat scan --headers <url>` checks security headers | Not Started
7 | 2.7 | Extend Result Aggregator | Add Module 2 scanner outputs to unified schema, severity-based exit codes, SARIF + JUnit XML export | 2d | Critical | 2.1,2.4,2.5 | Lead Dev | Unified report now includes security findings | Not Started
8 | 2.8 | Extend GitHub Actions Workflow | Add security scan jobs (parallel), configurable gate modes (block/warn/report-only), threshold config via env vars | 2d | Critical | 2.7 | Lead Dev | Updated `.github/workflows/dat.yml` with security gates | Not Started
PHASE 3: TEST INTELLIGENCE — AUTOMATED GENERATION & EXECUTION
Milestone: M3: AI-powered test generation running in CI, coverage reporting integrated into pipeline output
# | Task ID | Task Name | Description | Effort | Priority | Depends On | Owner | Deliverable | Status
1 | 3.1 | Qodo Cover-Agent Integration | Integrate open-source Cover-Agent: agentic loop that runs Jest, reads coverage, generates tests for uncovered lines, iterates | 4d | High | 1.2 | Dev 1 | `dat test --generate` produces coverage-driven test files | Not Started
2 | 3.2 | Jest Coverage Module | Run existing Jest test suite, parse coverage reports (lcov/JSON), identify uncovered functions and branches | 2d | Critical | 1.2 | Dev 2 | `dat test --coverage` reports coverage gaps per file | Not Started
3 | 3.3 | Keploy API Test Gen | Integrate Keploy for API regression testing: traffic capture, test case generation with mocks/stubs, replay validation | 3d | Medium | 1.2 | Dev 1 | `dat test --api-record` and `dat test --api-replay` | Not Started
4 | 3.4 | k6 Load Testing Module | Performance testing wrapper: configurable VUs, duration, thresholds. k6 script generation from OpenAPI spec if available. | 3d | Medium | 1.2 | Dev 2 | `dat test --load <url>` runs k6 with configurable thresholds | Not Started
5 | 3.5 | OpenTelemetry Trace Analysis | Parse OTel traces (Jaeger export) to identify latency bottlenecks, slow spans, and error-rate hotspots | 3d | Low | - | Dev 1 | `dat test --trace-analyze` reports top-N slow operations | Not Started
6 | 3.6 | Test Report Generator | Produce consolidated test report: coverage %, generated test count, load test p95/p99, pass/fail summary. JUnit XML export. | 2d | High | 3.1,3.2,3.4 | Lead Dev | Unified test report in JSON + JUnit XML | Not Started
7 | 3.7 | Extend GitHub Actions for Tests | Add test generation and execution jobs to CI pipeline, coverage thresholds as quality gates, test result annotations on PRs | 2d | High | 3.6 | Lead Dev | Test results visible in GitHub PR checks | Not Started
PHASE 4: AGGREGATION — DASHBOARD & FINDING MANAGEMENT
Milestone: M4: DefectDojo ingesting all scanner results, deployment readiness score computed per project
# | Task ID | Task Name | Description | Effort | Priority | Depends On | Owner | Deliverable | Status
1 | 4.1 | DefectDojo Deployment | Docker Compose setup for DefectDojo: PostgreSQL, Redis, Celery, Nginx. Initial product/engagement structure. | 2d | High | - | Dev 2 | DefectDojo running at internal URL with admin configured | Not Started
2 | 4.2 | Scanner Result Ingestion | Build import pipeline: convert each scanner's output to DefectDojo-compatible format, auto-upload via API after CI runs | 4d | Critical | 4.1,2.7,3.6 | Lead Dev | All findings from CI pipeline auto-imported into DefectDojo | Not Started
3 | 4.3 | Deployment Readiness Score | Compute weighted health score from dimensions: code quality, test coverage, security vulns, container health. Configurable weights. | 3d | High | 4.2 | Dev 1 | Score displayed in CLI output and DefectDojo product view | Not Started
4 | 4.4 | Dependency-Track Setup | Deploy Dependency-Track alongside DefectDojo for continuous SBOM monitoring, CycloneDX ingestion from Trivy/Syft | 2d | Medium | 4.1 | Dev 2 | Dependency-Track ingesting SBOMs from CI pipeline | Not Started
5 | 4.5 | Jira Integration | Configure DefectDojo-to-Jira sync: auto-create tickets for critical findings, bi-directional status sync | 2d | Medium | 4.2 | Dev 2 | Critical findings auto-create Jira tickets with details | Not Started
6 | 4.6 | PDF/CSV Report Export | CLI command to export aggregated findings as PDF and CSV from DefectDojo API, branded template for stakeholder distribution | 2d | Medium | 4.2 | Dev 1 | `dat report --export pdf` generates branded report | Not Started
7 | 4.7 | Grafana Dashboards (Optional) | Connect Grafana to DefectDojo via custom ETL script if native dashboards are insufficient. Time-series vulnerability trends. | 3d | Low | 4.2 | Dev 2 | Grafana dashboard showing vuln trends per project | Not Started
PHASE 5: INTELLIGENCE LAYER — FEEDBACK & ORG-SPECIFIC TUNING
Milestone: M5: LLM suggestion accuracy tracking live, org-specific Semgrep rules deployed, documentation complete
# | Task ID | Task Name | Description | Effort | Priority | Depends On | Owner | Deliverable | Status
1 | 5.1 | LLM Suggestion Feedback Loop | PR-Agent extension: capture accept/reject/modify on each suggestion, store structured feedback with taxonomy | 4d | Medium | 1.5 | Dev 1 | Feedback widget on PR comments, data stored for analysis | Not Started
2 | 5.2 | Custom Semgrep Rule Pack | Develop organisation-specific Semgrep rules based on internal coding standards, common anti-patterns found during rollout | 3d | High | 1.3 | Lead Dev | Published internal Semgrep rule pack on registry or repo | Not Started
3 | 5.3 | Feedback Analytics Dashboard | Aggregate feedback data: accuracy per suggestion type, false positive rate, improvement trends over time | 3d | Medium | 5.1,4.2 | Dev 2 | Analytics page showing LLM suggestion accuracy metrics | Not Started
4 | 5.4 | Language Support Matrix Documentation | Create and maintain versioned support matrix: which scanners support which languages, known gaps, community request tracker | 1d | Medium | - | Dev 1 | SUPPORTED_LANGUAGES.md in repo, linked from CLI help | Not Started
5 | 5.5 | End-to-End Integration Testing | Validate full pipeline against 3+ real JS/TS projects: scan, test, report, ingest, gate. Fix integration bugs. | 4d | Critical | 4.2,3.7 | Lead Dev | All 3 test projects pass full pipeline without errors | Not Started
6 | 5.6 | User Documentation & Onboarding | CLI usage docs, GitHub Action setup guide, DefectDojo onboarding guide, troubleshooting FAQ | 3d | High | 5.5 | Dev 2 | Complete docs site or README covering all features | Not Started
PHASE 6: LLM SECURITY & RED TEAMING
Milestone: M6: LLM-specific vulnerabilities (Prompt Injection, Jailbreaks) automatically blocked in CI
# | Task ID | Task Name | Description | Effort | Priority | Depends On | Owner | Deliverable | Status
1 | 6.1 | Promptfoo Integration | Implement Promptfoo adapter for CI-based prompt evaluation and semantic drift testing. | 3d | High | - | Dev 1 | dat scan --llm-eval | Not Started
2 | 6.2 | Garak Red-Teaming Scanner | Implement Garak DAST adapter to probe live LLM endpoints for injections and jailbreaks. | 4d | Critical | 6.1 | Dev 1 | dat scan --llm-redteam <url> | Not Started
3 | 6.3 | AI Secret Detection Rules | Custom Semgrep/Trivy rules to block HuggingFace, Pinecone, and Anthropic keys from codebase. | 2d | High | - | Lead Dev | Updated secret scanning ruleset | Not Started
4 | 6.4 | AI Quality Gate Integration | Wire LLM findings into AggregatedReport and CI/CD gate blocking logic. | 2d | Critical | 6.2 | Lead Dev | LLM findings fail GitHub Actions pipeline | Not Started

## Timeline
Project Timeline — Gantt View
# | Phase | Task | Effort | Owner | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21
[5 empty] | 07/07 | 14/07 | 21/07 | 28/07 | 04/08 | 11/08 | 18/08 | 25/08 | 01/09 | 08/09 | 15/09 | 22/09 | 29/09 | 06/10 | 13/10 | 20/10 | 27/10 | 03/11 | 10/11 | 17/11 | 24/11
PHASE 1: Foundation — Static Analysis & Container Security
1 | P1 | Project Initialisation | 2d | Lead Dev
2 | P1 | Scanner Execution Engine | 3d | Lead Dev
3 | P1 | Semgrep Integration | 2d | Dev 1
4 | P1 | SonarQube Integration | 3d | Dev 2
5 | P1 | PR-Agent Setup | 2d | Dev 1
6 | P1 | Hadolint Integration | 1d | Dev 2
7 | P1 | Trivy Container Scan | 2d | Dev 1
8 | P1 | Dockle Integration | 1d | Dev 2
9 | P1 | Result Aggregator v1 | 2d | Lead Dev
10 | P1 | GitHub Actions Workflow v1 | 2d | Lead Dev
11 | P1 | Console Reporter | 1d | Dev 1
| M1 | M1: All static analysis and container scanners run in GitHub Actions, producing SARIF output on every PR |  |  |  |  | ◆
PHASE 2: Security Depth — DAST, SCA, IaC Scanning
12 | P2 | Trivy SCA Module | 2d | Dev 1
13 | P2 | OSV-Scanner Integration | 1d | Dev 2
14 | P2 | Renovate Configuration | 2d | Dev 2
15 | P2 | Checkov IaC Scanner | 2d | Dev 1
16 | P2 | OWASP ZAP Baseline Scan | 3d | Dev 1
17 | P2 | Security Headers Checker | 1d | Dev 2
18 | P2 | Extend Result Aggregator | 2d | Lead Dev
19 | P2 | Extend GitHub Actions Workflow | 2d | Lead Dev
| M2 | M2: Full security scanning pipeline (SAST+DAST+SCA+IaC) running in CI with unified output | [7 empty] | ◆
PHASE 3: Test Intelligence — Automated Generation & Execution
20 | P3 | Qodo Cover-Agent Integration | 4d | Dev 1
21 | P3 | Jest Coverage Module | 2d | Dev 2
22 | P3 | Keploy API Test Gen | 3d | Dev 1
23 | P3 | k6 Load Testing Module | 3d | Dev 2
24 | P3 | OpenTelemetry Trace Analysis | 3d | Dev 1
25 | P3 | Test Report Generator | 2d | Lead Dev
26 | P3 | Extend GitHub Actions for Tests | 2d | Lead Dev
| M3 | M3: AI-powered test generation running in CI, coverage reporting integrated into pipeline output | [11 empty] | ◆
PHASE 4: Aggregation — Dashboard & Finding Management
27 | P4 | DefectDojo Deployment | 2d | Dev 2
28 | P4 | Scanner Result Ingestion | 4d | Lead Dev
29 | P4 | Deployment Readiness Score | 3d | Dev 1
30 | P4 | Dependency-Track Setup | 2d | Dev 2
31 | P4 | Jira Integration | 2d | Dev 2
32 | P4 | PDF/CSV Report Export | 2d | Dev 1
33 | P4 | Grafana Dashboards (Optional) | 3d | Dev 2
| M4 | M4: DefectDojo ingesting all scanner results, deployment readiness score computed per project | [15 empty] | ◆
PHASE 5: Intelligence Layer — Feedback & Org-Specific Tuning
34 | P5 | LLM Suggestion Feedback Loop | 4d | Dev 1
35 | P5 | Custom Semgrep Rule Pack | 3d | Lead Dev
36 | P5 | Feedback Analytics Dashboard | 3d | Dev 2
37 | P5 | Language Support Matrix Documentation | 1d | Dev 1
38 | P5 | End-to-End Integration Testing | 4d | Lead Dev
39 | P5 | User Documentation & Onboarding | 3d | Dev 2
| M5 | M5: LLM suggestion accuracy tracking live, org-specific Semgrep rules deployed, documentation complete | [19 empty] | ◆
PHASE 6: LLM Security & Red Teaming
40 | P6 | Promptfoo Integration | 3d | Dev 1
41 | P6 | Garak Red-Teaming Scanner | 4d | Dev 1
42 | P6 | AI Secret Detection Rules | 2d | Lead Dev
43 | P6 | AI Quality Gate Integration | 2d | Lead Dev
| M6 | M6: LLM-specific vulnerabilities (Prompt Injection, Jailbreaks) automatically blocked in CI | [22 empty] | ◆

## Tool Stack
Open-Source Tool Stack Reference
All tools are free and open-source. Total license cost: $0. Infrastructure cost: Docker host only.
# | Tool | Role | Module | License | Install Method | Notes & Caveats
Module 1
1 | SonarQube Community Build | Static analysis, code quality, bug detection | Module 1 | LGPL-3.0 | Docker (self-hosted) | No branch/PR analysis in free tier. Use Semgrep for PR-level feedback.
2 | Semgrep (OSS) | Fast security/pattern rules, custom org standards | Module 1 | LGPL-2.1 | pip install semgrep | Highly customizable. Replaces manual coding standards checklists.
3 | PR-Agent | AI-powered PR review and suggestions | Module 1 | Apache-2.0 | GitHub Action (self-hosted) | Requires LLM API key. Self-hostable for data sovereignty.
Module 2
4 | ZAP by Checkmarx (OWASP ZAP) | DAST, blackbox security scanning, header checks | Module 2 | Apache-2.0 | Docker / direct download | Scans running applications. Requires staging/preview deployment URL.
Modules 2 & 4
5 | Trivy | SCA, container scanning, IaC, secrets detection | Modules 2 & 4 | Apache-2.0 | brew install trivy / Docker | All-in-one scanner. Single binary covers dependencies, containers, IaC.
Module 2
6 | Checkov | Infrastructure-as-Code security scanning | Module 2 | Apache-2.0 | pip install checkov | 1000+ built-in policies. Replaces archived Terrascan.
7 | OSV-Scanner | Low false-positive dependency scanning | Module 2 | Apache-2.0 | go install / binary | Google-backed. Queries OSV database for known vulns.
8 | Renovate | Automated dependency update PRs | Module 2 | AGPL-3.0 | GitHub Action (self-hosted) | Auto-creates PRs for outdated/vulnerable packages. Replaces manual remediation.
Module 4
9 | Hadolint | Dockerfile linting and best practices | Module 4 | GPL-3.0 | brew install hadolint / Docker | Includes ShellCheck. Flags bloated layers, root user, unversioned tags.
10 | Dockle | Built image CIS benchmark scanning | Module 4 | Apache-2.0 | brew install dockle / Docker | Checks built images (not Dockerfiles). Complements Hadolint.
Module 3
11 | Qodo Cover-Agent | AI-driven test generation to increase coverage | Module 3 | Apache-2.0 | pip install cover-agent | Agentic loop: runs tests, reads coverage, generates new tests, repeats.
12 | Keploy | API regression test generation from traffic | Module 3 | Apache-2.0 | curl install / Docker | Captures live API traffic and converts to test cases with mocks.
13 | k6 (Grafana) | Load and performance testing | Module 3 | AGPL-3.0 | brew install k6 | Modern JMeter replacement. Scriptable in JS, CI-friendly.
14 | OpenTelemetry + Jaeger | Distributed tracing for bottleneck detection | Module 3 | Apache-2.0 | Docker Compose | Instrument services to find latency bottlenecks across boundaries.
Module 6
15 | DefectDojo | Finding aggregation, audit trail, compliance, Jira sync | Module 6 | BSD-3-Clause | Docker Compose | Ingests 200+ scanner formats. Replaces custom dashboard + remediation tracking.
16 | Dependency-Track | SBOM-based continuous vulnerability monitoring | Module 6 | Apache-2.0 | Docker Compose | Ingests CycloneDX/SPDX SBOMs from Trivy or Syft.
17 | Grafana | Visualization dashboards (optional overlay) | Module 6 | AGPL-3.0 | Docker / brew | Only needed if DefectDojo native UI is insufficient.
Phase 6
18 | Promptfoo | Automated prompt evaluation and semantic testing | Phase 6 | MIT | npm install -g promptfoo | Tests LLM outputs against predefined matrices in CI.
19 | Garak | LLM Red-Teaming and Vulnerability Scanner | Phase 6 | Apache-2.0 | pip install garak | Probes for Prompt Injections, Jailbreaks, and Model DoS.

## Feature Mapping
Original Feature Spec -> Reconstructed Module Mapping
12 original features consolidated into 6 practical modules. 4 features eliminated or deferred.
# | Orig. ID | Original Feature Name | Orig. Priority | Disposition | New Module | Reasoning
1 | F1 | LLM-Based Logical Flaw Detection | Critical | Restructured | Module 1 (PR-Agent) | PR-Agent provides LLM-driven code review on PRs. Pure logical flaw detection at scale is not reliably achievable without human verification. Semi-automated suggestions via PR-Agent are the practical equivalent.
2 | F2 | Code Optimisation & Re-configuration | Critical | Downgraded | Module 1 (PR-Agent + Renovate) | Fully automated remediation 'preserving functional equivalence' is unsolved. PR-Agent suggests fixes; Renovate auto-updates dependencies. Human review remains required for non-trivial changes.
3 | F3 | Code Review (Expanded) | High | Split into 4 modules | Modules 1, 2, 3 | Original F3 was 10 features in one. Static analysis -> Module 1. Security scanning -> Module 2. Test generation/execution -> Module 3. Design review -> PR-Agent.
4 | F4 | Security Headers Check (Blackbox) | High | Kept (simplified) | Module 2 | Dropped CheckMarx (paid) and Terrascan (archived). Replaced with ZAP + Trivy + Checkov. Added dedicated header checker.
5 | F5 | Vulnerability Scanning & Best-Fit Config | High | Merged with F4 | Module 2 | Dependency scanning is a subset of SCA already in Module 2 (Trivy + OSV-Scanner). Renovate handles the 'best-fit configuration' aspect via automated PRs.
6 | F6 | CI/CD Pipeline Integration | High | Kept (as glue layer) | Module 5 (cross-cutting) | Not a standalone feature — it is the delivery mechanism for all modules. Every module ships as a GitHub Action job. Composite workflow is Module 5.
7 | F7 | Docker Image Optimisation | Medium | Kept (simplified) | Module 4 | Dropped Codeaira dependency (proprietary). Hadolint + Trivy + Dockle cover linting, CVE scanning, and CIS benchmarks.
8 | F8 | Unified Dashboard & Reporting | Medium | Replaced by DefectDojo | Module 6 | DefectDojo provides finding aggregation, health scores, drill-down, export (PDF/CSV/JSON), and role-based views out of the box. No need to build custom.
9 | F9 | Remediation Tracking & Audit Trail | Medium | Replaced by DefectDojo | Module 6 | DefectDojo provides full finding lifecycle tracking (Open -> Resolved / Risk Accepted), audit trails, Jira integration, and SLA management natively.
10 | F10 | Multi-Language & Framework Support Matrix | Medium | Eliminated (docs only) | N/A — SUPPORTED_LANGUAGES.md | This is a documentation artifact, not a product feature. A maintained markdown file is sufficient.
11 | F11 | Developer Feedback Loop | Strategic | Deferred to Phase 5 | Phase 5 (v2) | Requires active user base generating signal first. Implemented as PR-Agent feedback extension in Phase 5.
12 | F12 | Accelerators Identification | Strategic | Deferred indefinitely | N/A — Research project | No existing open-source tooling supports automated reusable component identification with confidence scores. This is a research problem, not a product feature.

## Risk Register
Risk Register & Mitigation Plan
# | Risk ID | Risk Description | Impact | Probability | Mitigation Strategy | Owner | Status
1 | R1 | SonarQube Community lacks PR/branch analysis | High | Certain | Use Semgrep for PR-level scanning (fast, supports GitHub Actions natively). SonarQube reserved for main-branch baseline tracking. | Lead Dev | Mitigated
2 | R2 | LLM API costs for PR-Agent at scale | Medium | High | Start with rate-limited usage. Configure PR-Agent to only review PRs with >50 lines changed. Evaluate local models via Ollama for cost reduction. | Lead Dev | Monitor
3 | R3 | ZAP DAST requires running application | Medium | Certain | Only trigger ZAP scans on staging/preview deployments, not on every PR. Use Vercel/Netlify preview URLs or Docker Compose-based ephemeral environments. | Dev 1 | Mitigated
4 | R4 | False positive fatigue from multiple scanners | High | High | DefectDojo deduplication. Tune scanner thresholds (Critical/High only for gate blocking). Semgrep custom rules to suppress known false positives. | Lead Dev | Monitor
5 | R5 | AI-generated tests may not reflect business logic | Medium | High | All generated tests tagged as '[auto-generated]'. Require human review before merge. Cover-Agent used for coverage gaps, not business logic tests. | Dev 1 | Accepted
6 | R6 | DefectDojo infra overhead (PostgreSQL, Redis, Celery) | Medium | Medium | Use official Docker Compose deployment. Defer to Phase 4 when value is proven. Consider DefectDojo Cloud if self-hosting is burdensome. | Dev 2 | Monitor
7 | R7 | Terrascan is archived — spec references it | Low | Certain | Already replaced with Checkov in reconstructed plan. No action needed. | N/A | Mitigated
8 | R8 | KleanCode/Codeaira unavailable publicly | Medium | Certain | Eliminated as dependency. Replaced with PR-Agent (suggestions) + Renovate (dependency fixes). Manual remediation for complex changes. | N/A | Mitigated
9 | R9 | Team unfamiliar with multiple new tools simultaneously | Medium | Medium | Phased rollout. Each phase introduces max 3-4 tools. Internal brown-bag sessions after each milestone. | Lead Dev | Monitor
10 | R10 | Scope creep from original 12-feature spec | High | High | Feature map documents exactly what was cut and why. Phase 5 captures deferred items. Backlog grooming at each milestone gate. | Lead Dev | Monitor

## Effort Summary
Effort & Resource Summary
Effort by Phase
Phase | Name | Duration | Total Effort | Tasks | Critical Tasks | Milestone Week
Phase 1 | Foundation | 3 weeks | 21 days (4.2 wks) | 11 | 5 | Week 3
Phase 2 | Security Depth | 3 weeks | 15 days (3.0 wks) | 8 | 3 | Week 6
Phase 3 | Test Intelligence | 4 weeks | 19 days (3.8 wks) | 7 | 1 | Week 10
Phase 4 | Aggregation | 4 weeks | 18 days (3.6 wks) | 7 | 1 | Week 14
Phase 5 | Intelligence Layer | 4 weeks | 18 days (3.6 wks) | 6 | 1 | Week 18
Phase 6 | LLM Security & Red Teaming | 3 weeks | 11 days (2.2 wks) | 4 | 2 | Week 21
TOTAL |  | 21 weeks | 102 days (20.4 wks) | 43 | 13 | Week 21
Resource Allocation (Recommended)
Role | Responsibility | Phases Active | Est. Allocation | Skills Required
Lead Dev | Architecture, execution engine, result aggregation, CI pipeline, integration testing | 1-5 | 100% | TypeScript, CI/CD, DevSecOps pipeline design
Dev 1 | Scanner integrations (Semgrep, Trivy, ZAP, Cover-Agent, Keploy), console reporter | 1-5 | 100% | TypeScript, security tooling, testing frameworks
Dev 2 | Scanner integrations (SonarQube, Hadolint, Dockle, Checkov), DefectDojo, Grafana, docs | 1-5 | 80% | Docker, infrastructure, DevOps, documentation
Key Assumptions
1. Team of 3 (1 Lead + 2 Developers) working full-time on this project.
2. All tools installed via Docker or package managers — no enterprise license procurement delays.
3. GitHub Actions is the primary CI/CD platform. GitLab/Jenkins templates are secondary deliverables.
4. Target projects are JavaScript/TypeScript. Multi-language support is Phase 5+ scope.
5. LLM API key (OpenAI or compatible) is available for PR-Agent and Cover-Agent integrations.
6. Staging/preview deployment environment exists for DAST (ZAP) scanning.
7. Effort estimates assume familiarity with TypeScript and basic DevOps tooling.
8. Timelines are generalised — actual durations will vary based on team velocity and blockers.

## Future Roadmap
DAT: Current State (V2) & Future Trajectory (V3+)
# | Original Feature | Current Implementation (V2) | Future Roadmap (V3 / Backlog)
1 | F1 | LLM Flaw Detection | COMPLETED (V2): Autonomous Agents that clone repo, fix flaws, and submit PRs. | N/A - Fully Implemented
2 | F2 | Auto-Remediation | COMPLETED (V2): AST Auto-Fixers (ast-grep) to rewrite unsafe code automatically. | N/A - Fully Implemented
3 | F3 | Expanded Code Review | COMPLETED (V2): Ephemeral Env Scanning via Vercel integration, running dynamic ZAP/k6 tests. | N/A - Fully Implemented
4 | F4/F5 | Security & Vulns | COMPLETED (V2): Reachability Analysis engine natively verifying call paths for Node and Python. | N/A - Fully Implemented
5 | F6 | CI/CD Integration | COMPLETED (V2): Native GitHub App architecture via Probot for 1-click org installs and webhook triggers. | N/A - Fully Implemented
6 | F7 | Docker Optimisation | COMPLETED (V2): Auto-Distroless logic using LLM to dynamically rewrite vulnerable Dockerfiles. | N/A - Fully Implemented
7 | F8/F9 | Dashboard & Audit | DefectDojo integration & CLI Readiness Score. | Spotify Backstage Plugin: Embed DAT scores directly into org Internal Developer Portal.
8 | F10 | Language Matrix | COMPLETED (V2): Node.js, Python (Bandit/pip-audit), and Go (gosec/govulncheck) ecosystems. | Expansion to Tier 2 (Java/C#) and Tier 3 (Rust) ecosystems.
9 | F11 | Dev Feedback Loop | Telemetry script scaffolding. | Custom LoRA Fine-Tuning: Train local LLMs to learn the org's specific coding style.
10 | F12 | Accelerator ID | Deferred (Research concept). | Cross-Repo AST Search: Scan GitHub org for duplicated logic to build shared packages.
Language & Framework Expansion Tiers
Tier | Languages | Target Frameworks | Status / Required Security Scanners
Tier 1 (Months 1-3) | Python, Go (Golang) | FastAPI, Django, LangChain, Gin, Fiber | COMPLETED (V2): Bandit, pip-audit, gosec, govulncheck natively integrated.
Tier 2 (Months 3-6) | Java / Kotlin, C# / .NET | Spring Boot, Quarkus, ASP.NET Core | SpotBugs, OWASP Dependency-Check, SecurityCodeScan
Tier 3 (Months 6+) | Rust | Actix, Tokio | cargo-audit, clippy